## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | 1.1 | Installed JDK 21+ and set JAVA_HOME. | Must Have | None | Utkarsh Kumar Maurya | Done
| Sprint 1 | 1.2 | Created Maven project 'BankingSimulation' and verified mvn clean install. | Must Have | 1.1 | Utkarsh Kumar Maurya | Done
Sprint 2 | Sprint 2 | 2.1 | Installed MySQL Server 8.0 and created 'bankdb' database. | Must Have | 1.2 | Utkarsh Kumar Maurya | Done
| Sprint 2 | 2.2 | Added mysql-connector-java dependency to pom.xml. | Must Have | 2.1 | Utkarsh Kumar Maurya | Done
| Sprint 2 | 2.3 | Configured application.properties for DB credentials and URL. | Must Have | 2.1,2.2 | Utkarsh Kumar Maurya | Done
| Sprint 2 | 2.4 | Implemented DBConfig class to manage MySQL connection pooling. | Must Have | 2.3 | Utkarsh Kumar Maurya | Done
Sprint 3 | Sprint 3 | 3.1 | Created POJO classes for Customer, Account, Transaction. | Must Have | 2.4 | Utkarsh Kumar Maurya | Done
| Sprint 3 | 3.2 | Implemented schema creation scripts for tables: customers, accounts, transactions. | Must Have | 3.1 | Utkarsh Kumar Maurya | Done
Sprint 4 | Sprint 4 | 4.1 | Developed CustomerRepoImpl with full CRUD using PreparedStatements. | Must Have | 3.2 | Utkarsh Kumar Maurya | Done
| Sprint 4 | 4.2 | Added SQLException handling in repositories via custom exceptions. | Should Have | 4.1 | Utkarsh Kumar Maurya | Done
| Sprint 4 | 4.3 | Tested CustomerRepoImpl operations using dummy data. | Must Have | 4.1,4.2 | Utkarsh Kumar Maurya | Done
Sprint 5 | Sprint 5 | 5.1 | Installed Apache Tomcat 10 and deployed WAR file. | Must Have | 4.3 | Utkarsh Kumar Maurya | Done
| Sprint 5 | 5.2 | Configured Jersey servlet for REST APIs in web.xml. | Must Have | 5.1 | Utkarsh Kumar Maurya | Done
| Sprint 5 | 5.3 | Added required Jakarta dependencies for servlet, hk2, and JSON mapping. | Must Have | 5.1 | Utkarsh Kumar Maurya | Done
Sprint 6 | Sprint 6 | 6.1 | Implemented Customer APIs (CRUD) with validation and exception handling. | Must Have | 5.2 | Utkarsh Kumar Maurya | Done
| Sprint 6 | 6.2 | Added name, phone, and Aadhar validations in CustomerServiceImpl. | Must Have | 6.1 | Utkarsh Kumar Maurya | Done
| Sprint 6 | 6.3 | Implemented GlobalExceptionHandler for consistent API error responses. | Should Have | 6.1 | Utkarsh Kumar Maurya | Done
Sprint 7 | Sprint 7 | 7.1 | Implemented AccountServiceImpl for open, close, deposit, withdraw. | Must Have | 6.1 | Utkarsh Kumar Maurya | Done
| Sprint 7 | 7.2 | Developed AccountController REST APIs with DTO mappings. | Must Have | 7.1 | Utkarsh Kumar Maurya | Done
| Sprint 7 | 7.3 | Created custom exceptions for account operations. | Should Have | 7.2 | Utkarsh Kumar Maurya | Done
Sprint 8 | Sprint 8 | 8.1 | Implemented TransactionServiceImpl with JDBC transaction management. | Must Have | 7.3 | Utkarsh Kumar Maurya | Done
| Sprint 8 | 8.2 | Developed TransactionController for fund transfers. | Must Have | 8.1 | Utkarsh Kumar Maurya | Done
| Sprint 8 | 8.3 | Added validations and sender verification logic. | Must Have | 8.1 | Utkarsh Kumar Maurya | Done
Sprint 9 | Sprint 9 | 9.1 | Implemented CSV export for transaction history. | Should Have | 8.3 | Utkarsh Kumar Maurya | Done
| Sprint 9 | 9.2 | Created Login frontend using React integrated with backend Auth API. | Must Have | 8.3 | Utkarsh Kumar Maurya | Done
Sprint 10 | Sprint 10 | 10.1 | Added dynamic UI for managing customers, accounts, transactions. | Must Have | 9.2 | Utkarsh Kumar Maurya | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7