## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Utkarsh Kumar Maurya | 11-09-2025 | "Public Key Retrieval is not allowed" MySQL connection error. | Sprint-2 | Utkarsh Kumar Maurya | Code (Configuration) | Added allowPublicKeyRetrieval=true to JDBC URL. | 11-09-2025 | Closed | Resolved MySQL 8+ key retrieval issue.
2 | Utkarsh Kumar Maurya | 16-09-2025 | No operations allowed after connection closed. | Sprint-4 | Utkarsh Kumar Maurya | Code (Configuration) | DBConfig modified to return new connection instance. | 16-09-2025 | Closed | Connection was being reused and closed.
3 | Utkarsh Kumar Maurya | 20-09-2025 | JAR packaging prevented Tomcat deployment. | Sprint-5 | Utkarsh Kumar Maurya | Build Configuration | Changed pom.xml packaging to WAR. | 20-09-2025 | Closed | Deployed successfully on Tomcat.
4 | Utkarsh Kumar Maurya | 22-09-2025 | Customer validation failed due to invalid regex. | Sprint-6 | Utkarsh Kumar Maurya | Validation | Updated regex to allow spaces in names. | 22-09-2025 | Closed | Regex adjusted for valid names.
5 | Utkarsh Kumar Maurya | 29-09-2025 | Transfer transaction failed due to missing auto-commit. | Sprint-7 | Utkarsh Kumar Maurya | Code (Transaction) | Implemented manual transaction handling. | 29-09-2025 | Closed | Transactions handled successfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others